## Dashboard
PROJECT MANAGEMENT DASHBOARD |  |  |  |  | 17-Feb-20 to 16-Mar-20
Projects | Task | Manager | Start Date | Days Completed | End Date | Progress | Duration | Budget | Actual | 2020-02-17 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | 2020-02-22 | 2020-02-23 | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-02-29 | 2020-03-01 | 2020-03-02 | 2020-03-03
CP | Task 1 | Ladd | 2020-02-19 | 3 | 2020-02-24 | 100% | 3 | 817000 | 807069
| Task 2 | Hirsch | 2020-02-21 | 3 | 2020-03-03 | 42.86% | 7 | 372000 | 173166
| Task 3 | Samora | 2020-02-24 | 2 | 2020-03-09 | 20% | 10 | 50000 | 8400
| Task 4 | McFay | 2020-02-24 | 3 | 2020-03-09 | 30% | 10 | 807000 | 262679
| Task 5 | Wood | 2020-02-24 | 0 | 2020-02-27 | 0% | 3 | 691000 | 0
| Task 6 | Ladd | 2020-02-25 | 0 | 2020-03-05 | 0% | 7 | 50678 | 0
| Task 7 | Hirsch | 2020-02-26 | 3 | 2020-03-04 | 60% | 5 | 20000 | 13000
Data Analyst | Task 1 | McFay | 2020-02-17 | 5 | 2020-03-02 | 50% | 10 | 839000 | 406974
| Task 2 | Wood | 2020-02-21 | 4 | 2020-02-28 | 80% | 5 | 729000 | 487139
| Task 3 | Ladd | 2020-02-24 | 3 | 2020-03-04 | 42.86% | 7 | 826000 | 298186
| Task 4 | McFay | 2020-02-26 | 2 | 2020-03-06 | 28.57% | 7 | 895000 | 280583
| Task 5 | Wood | 2020-02-28 | 2 | 2020-03-04 | 66.67% | 3 | 341000 | 129785
| Task 6 | Ladd | 2020-03-02 | 8 | 2020-03-13 | 88.89% | 9 | 787000 | 727188
| Task 7 | Hirsch | 2020-03-02 | 2 | 2020-03-16 | 20% | 10 | 228000 | 47880
| Task 8 | McFay | 2020-03-03 | 2 | 2020-03-10 | 40% | 5 | 50000 | 30000
Excel | Task 1 | McFay | 2020-02-17 | 2 | 2020-02-24 | 40% | 5 | 218000 | 97337
| Task 10 | Samora | 2020-02-24 | 3 | 2020-03-03 | 50% | 6 | 416000 | 175015
| Task 2 | Wood | 2020-02-17 | 3 | 2020-02-25 | 50% | 6 | 393000 | 177440
| Task 3 | Ladd | 2020-02-18 | 4 | 2020-03-03 | 40% | 10 | 86000 | 31046
| Task 4 | Hirsch | 2020-02-21 | 3 | 2020-03-05 | 33.33% | 9 | 732000 | 261324
| Task 5 | Samora | 2020-02-17 | 1 | 2020-02-21 | 25% | 4 | 492000 | 116850
| Task 6 | McFay | 2020-02-20 | 0 | 2020-02-28 | 0% | 6 | 188000 | 0
| Task 7 | Wood | 2020-02-20 | 3 | 2020-03-02 | 42.86% | 7 | 180000 | 79380
| Task 8 | Ladd | 2020-02-24 | 2 | 2020-03-02 | 40% | 5 | 582000 | 195231
| Task 9 | Hirsch | 2020-02-24 | 1 | 2020-03-06 | 11.11% | 9 | 562000 | 74746
ML | Task 1 | McFay | 2020-02-18 | 7 | 2020-02-27 | 100% | 7 | 293000 | 273001
| Task 10 | Samora | 2020-02-17 | 3 | 2020-02-20 | 100% | 3 | 68000 | 64987
| Task 2 | Wood | 2020-02-17 | 4 | 2020-02-28 | 44.44% | 9 | 224000 | 57910
| Task 3 | Ladd | 2020-02-18 | 0 | 2020-02-28 | 0% | 8 | 978000 | 0
| Task 4 | Hirsch | 2020-02-20 | 3 | 2020-03-02 | 42.86% | 7 | 932000 | 379157
| Task 5 | Samora | 2020-02-21 | 1 | 2020-02-27 | 25% | 4 | 854000 | 322812
| Task 6 | McFay | 2020-02-21 | 3 | 2020-03-02 | 50% | 6 | 81000 | 38461
| Task 7 | Wood | 2020-02-24 | 5 | 2020-03-03 | 83.33% | 6 | 169000 | 136468
| Task 8 | Ladd | 2020-02-25 | 1 | 2020-03-02 | 25% | 4 | 61000 | 12078
| Task 9 | Hirsch | 2020-02-27 | 3 | 2020-03-09 | 42.86% | 7 | 645000 | 273048
Web D | Task 1 | Samora | 2020-02-17 | 0 | 2020-02-21 | 0% | 4 | 147000 | 0
| Task 2 | McFay | 2020-02-19 | 5 | 2020-03-02 | 62.5% | 8 | 338000 | 205123
| Task 3 | Wood | 2020-02-24 | 3 | 2020-03-09 | 30% | 10 | 857000 | 305949
| Task 4 | Ladd | 2020-02-25 | 3 | 2020-03-04 | 50% | 6 | 602000 | 322371
| Task 5 | Hirsch | 2020-02-25 | 2 | 2020-03-02 | 50% | 4 | 990000 | 451440
| Task 6 | Samora | 2020-02-28 | 3 | 2020-03-11 | 37.5% | 8 | 96000 | 32256
| Task 7 | McFay | 2020-03-02 | 6 | 2020-03-13 | 66.67% | 9 | 513000 | 226233
| Task 8 | Wood | 2020-02-20 | 3 | 2020-02-27 | 60% | 5 | 616000 | 401579
Grand Total | [7 empty] | 19815678 | 8383291
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## workings
Task Bar Chart |  | Overall Progress- Days Completed vs Duration
Not Started | 5 | Values |  | Donut Chart | % |  | Budget | Actual | Scroll Bar
Inprogress | 35 | Sum of Days Completed | 119 | Days completed | 42.05% | Bar Chart | 19815678 | 8383291 | 0
Completed | 3 | Sum of Duration | 283 | Days Remaining | 57.95% | Donut Chart | 42.31% | 57.69%
Remaining | 40
Total | 43

## Data
Projects | Task | Manager | Start Date | Duration | End Date | Days Completed | Progress | Budget | Actual
Excel | Task 1 | McFay | 2020-02-17 | 5 | 2020-02-24 | 2 | 40% | 218000 | 97337
Excel | Task 2 | Wood | 2020-02-17 | 6 | 2020-02-25 | 3 | 50% | 393000 | 177440
Excel | Task 3 | Ladd | 2020-02-18 | 10 | 2020-03-03 | 4 | 40% | 86000 | 31046
Excel | Task 4 | Hirsch | 2020-02-21 | 9 | 2020-03-05 | 3 | 33.33% | 732000 | 261324
Excel | Task 5 | Samora | 2020-02-17 | 4 | 2020-02-21 | 1 | 25% | 492000 | 116850
Excel | Task 6 | McFay | 2020-02-20 | 6 | 2020-02-28 | 0 | 0% | 188000 | 0
Excel | Task 7 | Wood | 2020-02-20 | 7 | 2020-03-02 | 3 | 42.86% | 180000 | 79380
Excel | Task 8 | Ladd | 2020-02-24 | 5 | 2020-03-02 | 2 | 40% | 582000 | 195231
Excel | Task 9 | Hirsch | 2020-02-24 | 9 | 2020-03-06 | 1 | 11.11% | 562000 | 74746
Excel | Task 10 | Samora | 2020-02-24 | 6 | 2020-03-03 | 3 | 50% | 416000 | 175015
ML | Task 1 | McFay | 2020-02-18 | 7 | 2020-02-27 | 7 | 100% | 293000 | 273001
ML | Task 2 | Wood | 2020-02-17 | 9 | 2020-02-28 | 4 | 44.44% | 224000 | 57910
ML | Task 3 | Ladd | 2020-02-18 | 8 | 2020-02-28 | 0 | 0% | 978000 | 0
ML | Task 4 | Hirsch | 2020-02-20 | 7 | 2020-03-02 | 3 | 42.86% | 932000 | 379157
ML | Task 5 | Samora | 2020-02-21 | 4 | 2020-02-27 | 1 | 25% | 854000 | 322812
ML | Task 6 | McFay | 2020-02-21 | 6 | 2020-03-02 | 3 | 50% | 81000 | 38461
ML | Task 7 | Wood | 2020-02-24 | 6 | 2020-03-03 | 5 | 83.33% | 169000 | 136468
ML | Task 8 | Ladd | 2020-02-25 | 4 | 2020-03-02 | 1 | 25% | 61000 | 12078
ML | Task 9 | Hirsch | 2020-02-27 | 7 | 2020-03-09 | 3 | 42.86% | 645000 | 273048
ML | Task 10 | Samora | 2020-02-17 | 3 | 2020-02-20 | 3 | 100% | 68000 | 64987
Data Analyst | Task 1 | McFay | 2020-02-17 | 10 | 2020-03-02 | 5 | 50% | 839000 | 406974
Data Analyst | Task 2 | Wood | 2020-02-21 | 5 | 2020-02-28 | 4 | 80% | 729000 | 487139
Data Analyst | Task 3 | Ladd | 2020-02-24 | 7 | 2020-03-04 | 3 | 42.86% | 826000 | 298186
Data Analyst | Task 4 | McFay | 2020-02-26 | 7 | 2020-03-06 | 2 | 28.57% | 895000 | 280583
Data Analyst | Task 5 | Wood | 2020-02-28 | 3 | 2020-03-04 | 2 | 66.67% | 341000 | 129785
Data Analyst | Task 6 | Ladd | 2020-03-02 | 9 | 2020-03-13 | 8 | 88.89% | 787000 | 727188
Data Analyst | Task 7 | Hirsch | 2020-03-02 | 10 | 2020-03-16 | 2 | 20% | 228000 | 47880
Web D | Task 1 | Samora | 2020-02-17 | 4 | 2020-02-21 | 0 | 0% | 147000 | 0
Web D | Task 2 | McFay | 2020-02-19 | 8 | 2020-03-02 | 5 | 62.5% | 338000 | 205123
Web D | Task 3 | Wood | 2020-02-24 | 10 | 2020-03-09 | 3 | 30% | 857000 | 305949
Web D | Task 4 | Ladd | 2020-02-25 | 6 | 2020-03-04 | 3 | 50% | 602000 | 322371
Web D | Task 5 | Hirsch | 2020-02-25 | 4 | 2020-03-02 | 2 | 50% | 990000 | 451440
Web D | Task 6 | Samora | 2020-02-28 | 8 | 2020-03-11 | 3 | 37.5% | 96000 | 32256
Web D | Task 7 | McFay | 2020-03-02 | 9 | 2020-03-13 | 6 | 66.67% | 513000 | 226233
Web D | Task 8 | Wood | 2020-02-20 | 5 | 2020-02-27 | 3 | 60% | 616000 | 401579
CP | Task 1 | Ladd | 2020-02-19 | 3 | 2020-02-24 | 3 | 100% | 817000 | 807069
CP | Task 2 | Hirsch | 2020-02-21 | 7 | 2020-03-03 | 3 | 42.86% | 372000 | 173166
CP | Task 3 | Samora | 2020-02-24 | 10 | 2020-03-09 | 2 | 20% | 50000 | 8400
CP | Task 4 | McFay | 2020-02-24 | 10 | 2020-03-09 | 3 | 30% | 807000 | 262679
CP | Task 5 | Wood | 2020-02-24 | 3 | 2020-02-27 | 0 | 0% | 691000 | 0
CP | Task 6 | Ladd | 2020-02-25 | 7 | 2020-03-05 | 0 | 0% | 50678 | 0
CP | Task 7 | Hirsch | 2020-02-26 | 5 | 2020-03-04 | 3 | 60% | 20000 | 13000
Data Analyst | Task 8 | McFay | 2020-03-03 | 5 | 2020-03-10 | 2 | 40% | 50000 | 30000
Formulas:
End Date = WORKDAY.INTL([Start Date],[Duration],1,)